## categories
id | name | description
1 | Frontend | UI components and client-side features
2 | Backend | Server-side logic and database tasks
3 | Design | Visual and UX design tasks
4 | Integration | Third-party services and APIs
5 | E-Commerce | Online store features and product catalog
6 | Custom Tools | Configurators
7 | Performance & Security | Optimization
8 | SEO & Content | Blog setup
9 | Local SEO | This category is for the company that would want local Visibility for their website.
10 | SEO on-page | On-page SEO is how you optimize a webpage so
11 | SEO off-page | Off-page SEO is everything done outside your website t
12 | Conversion Tracking | Conversion tracking is the process of measuring
13 | Environment Setup | Setting up Environment for Stagin and Deployment of Content and files
14 | Deployment
15 | CMS & Content Prep
16 | Pre-Lanuch
17 | Post-Launch
18 | Database

## Word Press
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services or Product Grid | 1 | 3 | Grid layout for displaying services, products, programs, or offerings (including nonprofit initiatives or services).
3 |  | Homepage – Standard | Testimonials Slider-Dynamic | 1 | 8 | Dynamic testimonials integration via external API (e.g., review platforms), not embed-based
4 |  | Homepage – Standard | Testimonials Slider- embed | 1 | 3 | Embedded testimonials using iframe or widget from external platforms.
5 |  | Homepage – Standard | Team Preview | 1 | 1.5 | Section highlighting team members, staff, or key representatives
6 |  | Homepage – Standard | Footer Layout | 1 | 1.5 | Structured footer with navigation and contact info
7 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Strong hero offer with CTA
8 |  | Homepage – Conversion | Benefits/Features | 1 | 3 | Highlight product/service benefits
9 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Section showcasing logos, trust badges, or affiliations to build credibility, reinforce trust, and support conversion.
10 |  | Homepage – Conversion | FAQ Section | 1 | 2 | Frequently asked questions block
11 |  | Homepage – Standard | Pricing Tables | 1 | 4 | Structured plans with features and comparison layout
12 |  | Homepage – Standard | Galleries | 1 | 2 | Image gallery layout for showcasing media (grid, slider, or lightbox)
13 |  | Homepage – Standard | Video embeds | 1 | 1 | Embedded videos from platforms like YouTube or Vimeo
14 |  | Homepage - Standard | Payment / Contribution Module | 1 | 5 | Payment or contribution functionality using plugin-based integration (e.g., Stripe/PayPal), no custom gateway.
15 |  | Homepage - Standard | Use Cases | 1 | 2 | Real-world scenarios or examples demonstrating how offerings are used
16 |  | Homepage – Multi-Industry | Industry Selector | 1 | 8 | Selector for multiple industries
17 |  | Homepage – Multi-Industry | Location Selector | 1 | 8 | Selector for multiple branches/locations
18 |  | Homepage – Multi-Industry | Dynamic Content Sections | 1 | 10 | Conditional content per audience
19 |  | Homepage – Multi-Industry | Interactive Location Finder | 1 | 12 | Map or location-based finder for offices, stores, or service areas
20 |  | Homepage – Multi-Industry | Multi-Audience Messaging | 1 | 12 | Content tailored to different audience segments or user types
21 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 8 | Standard Content Page (About, Services, etc.)
22 |  | Core Page - Landing Page | Conversion Page | 1 | 8 | Conversion-focused landing page designed to drive specific user actions (e.g., lead generation or sales), including structured sections such as hero, benefits, social proof, and strong CTAs using a reusable layout.
23 |  | Core Page - Contact Page | Form or contact details page | 1 | 6 | Contact page including form setup and/or business contact details, with clear layout, validation, and user-friendly structure for inquiries or lead capture.
24 |  | Core Page - Detail Pages | Detail Template | 1 | 6 | Template-based detail page for individual content (e.g., blog posts or service pages), structured for readability, SEO, and consistent layout
25 |  | Homepage – Standard | Forms Spam Protection (reCAPTCHA) | 1 | 1 | Implement and configure reCAPTCHA (v2/v3) on all forms to prevent spam submissions.
26 |  | Homepage – Advanced Dynamic | Custom-Coded Blocks | 2 | 15 | Custom reusable blocks
27 |  | Homepage – Advanced Dynamic | Search Bar with Filters | 2 | 18 | Advanced search and filter functionality
28 |  | Homepage – Advanced Dynamic | API-Driven Content | 2 | 15 | Dynamic content via API
29 |  | Homepage – Advanced Dynamic | Interactive Dashboard | 2 | 18 | Custom dashboard with charts
30 |  | Homepage – Creative | Full-Screen Visuals | 3 | 6 | Image-heavy hero visuals
31 |  | Homepage – Creative | Parallax Effects | 3 | 5 | Scrolling parallax animations
32 |  | Homepage – Creative | Hover Animations | 3 | 4 | Interactive hover effects
33 |  | Homepage – Creative | Creative Grid Layouts | 3 | 5 | Custom creative grids
34 |  | Homepage – Creative | Portfolio Gallery Preview | 3 | 5 | Portfolio showcase gallery
35 |  | Homepage – Conversion | Lead Capture Form | 4 | 2 | Form placement within page for lead capture using standard form setup (no CRM unless specified)
36 |  | Homepage – E-Commerce | Live Chat Widget | 4 | 3 | Integration of live chat support
37 |  | Homepage – Advanced Dynamic | Multi-Step Wizard Form | 4 | 20 | Interactive multi-step form wizard. Custom or plugin-based depending on scope.
38 |  | Forms – Standard | Standard form setup including layout, validation, and email notifications for submissions | 4 | 3 | Setup of 1 standard form with layout, validation, and email notifications.
39 |  | Forms – Multi-Step | Multi-Step Layout | 4 | 4 | Multi-step form with branching logic
40 |  | Forms – Multi-Step | Branch Logic Implementation | 4 | 4 | Conditional branching between steps
41 |  | Forms – Multi-Step | Submission Handling | 4 | 2 | Store and process multi-step submissions
42 | 37-40: Form Setup | Forms – CRM Integration | CRM API Setup | 4 | 4 | Connect form submissions to CRM
43 | 37-40: Form Setup | Forms – CRM Integration | Data Mapping | 4 | 2 | Map form fields to CRM fields
44 | 37-40: Form Setup | Forms – CRM Integration | Error Handling & Logging | 4 | 2 | Handle API errors and log submissions
45 |  | Integrations | Appointment System | 4 | 3 | Booking and scheduling system. Plugin-based booking system (no custom development)
46 |  | Integrations | Live Chat Integration | 4 | 2 | Embed live chat widget
47 |  | Integrations | API Integration Basic | 4 | 12 | Simple API Integration
48 |  | Integrations | API Integration Complex | 4 | 25 | Complex API Integration
49 |  | Integrations | Zapier Workflows | 4 | 6 | Automate workflows with Zapier
50 |  | Integrations | Accessibility (ADA) Basic | 4 | 6 | Essential fixes for usability (alt text, contrast, basic keyboard support)
51 |  | Integrations | Accessibility (ADA) Strict Compliance | 4 | 25 | Full WCAG compliance with complete support and thorough testing
52 |  | Member Login | Basic Login System | 4 | 10 | User login and registration
53 |  | Member Login | Profile Management | 4 | 10 | Basic profile editing and updates
54 |  | Member Login | Role-Based Content | 4 | 12 | Restrict content based on user roles
55 |  | Member Login | Document Portal Setup | 4 | 20 | Portal for uploading and accessing documents. Plugin-based solution (no custom-built portal)
56 |  | E-Commerce | Product Template | 5 | 7 | Product page template
57 |  | E-Commerce | Featured Products | 5 | 6 | Homepage products
58 |  | E-Commerce | Sales Banners | 5 | 5 | Promo banners
59 |  | E-Commerce | Dynamic Product Feeds | 5 | 8 | Product listings
60 |  | E-Commerce | Category Highlights | 5 | 6 | Product categories
61 |  | E-Commerce | Customer Reviews | 5 | 6 | Reviews
62 |  | E-Commerce | Personalization Blocks | 5 | 6 | Recommendations
63 |  | E-Commerce | Cart Functionality | 5 | 5 | Add to cart
64 |  | E-Commerce | Checkout Flow | 5 | 8 | Checkout page
65 |  | E-Commerce | Shipping Rules | 5 | 6 | Shipping setup
66 |  | E-Commerce | Payment Gateway Integration | 5 | 5 | Stripe/PayPal
67 |  | E-Commerce | Tax Calculator | 5 | 4 | Tax logic
68 |  | E-Commerce | Product Variations Bsic Set-up | 5 | 3 | Configure product variations (size, color, attributes) using WooCommerce native options
69 |  | E-Commerce | Per product w/ variations | 5 | 0.5 | Per product w/ variations, need to multiply how many products with variations
70 |  | E-Commerce | Advanced Product Options (Plugin) | 5 | 6 | Add custom product fields/options using plugin (no custom build)
71 |  | E-Commerce | Product Add-Ons (Conditional Logic) | 5 | 8 | Product add-ons with conditional logic using plugin (e.g., extras, upgrades)
72 |  | E-Commerce | Subscriptions Setup | 5 | 6 | Setup recurring payments using WooCommerce Subscriptions plugin
73 |  | E-Commerce | Discount Rules / Coupons Setup | 5 | 4 | Configure coupons, discounts, and basic promotional rules using WooCommerce
74 |  | E-Commerce | Advanced Pricing Rules (Plugin) | 5 | 8 | Role-based pricing, bulk discounts, or dynamic pricing via plugin
75 |  | E-Commerce | Product Bundles / Packages | 5 | 6 | Create bundled or grouped products using plugin
76 |  | E-Commerce | Wishlist Functionality | 5 | 4 | Add wishlist feature via plugin
77 |  | E-Commerce | Product Filtering (Advanced) | 5 | 6 | Advanced filters (price, attributes, categories) using plugin
78 |  | Configurator – Basic 2D | Color Change Feature | 6 | 15 | Allow users to change product colors
79 |  | Configurator – Basic 2D | Shape Options | 6 | 20 | Simple shape selection and preview
80 |  | Configurator – Basic 2D | Static Preview Rendering | 6 | 30 | Generate static preview images
81 |  | Configurator – Advanced 2D | Pattern Library | 6 | 30 | Apply patterns to product surfaces
82 |  | Configurator – Advanced 2D | Upload & Download Assets | 6 | 30 | Allow users to upload images and download previews
83 |  | Configurator – Advanced 2D | Screenshot Capture | 6 | 40 | Enable screenshot capture of designs
84 |  | Configurator – 3D WebGL | Camera Controls | 6 | 40 | Interactive camera movement and zoom
85 |  | Configurator – 3D WebGL | 3D Asset Integration | 6 | 50 | Import and render 3D models
86 |  | Configurator – 3D WebGL | Real-Time Rendering | 6 | 55 | Real-time rendering of product visuals
87 |  | Configurator – Full Builder | Court/Template Setup | 6 | 80 | Custom templates for courts or products
88 |  | Configurator – Full Builder | Measurement Tools | 6 | 80 | Tools for measuring dimensions
89 |  | Configurator – Full Builder | Quote Generation | 6 | 80 | Auto-generate quotes based on design
90 |  | Configurator – Full Builder | User Accounts & Saved Designs | 6 | 80 | Allow users to save and manage designs
91 |  | Configurator – Features | Logo Upload & Placement | 6 | 12 | Upload logos and place them on designs
92 |  | Configurator – Features | Size Calculator | 6 | 15 | Calculate product sizes dynamically
93 |  | Configurator – Features | Shareable Link | 6 | 12 | Generate shareable links for designs
94 |  | Configurator – Features | Admin Dashboard | 6 | 44 | Admin dashboard for managing designs and users
95 |  | Performance & Security | SSL Configuration | 7 | 1 | Setup SSL certificate
96 |  | Performance & Security | Caching & Speed Optimization | 7 | 8 | Basic performance optimization using caching, image compression, and plugin configuration (no advanced code-level optimization)
97 |  | Performance & Security | Backup & Versioning | 7 | 2 | Setup backups and version control
98 |  | Analytics & Tracking | GA4 Setup | 7 | 2 | Configure Google Analytics 4 tracking
99 |  | Analytics & Tracking | GTM Setup | 7 | 3 | Install and configure Google Tag Manager
100 |  | Analytics & Tracking | Heatmaps | 7 | 1 | Integrate heatmap tool for user behavior analysis
101 |  | Blog Setup | Blog Listing Page | 8 | 2 | Main blog page with article previews
102 |  | Blog Setup | Single Article Template | 8 | 2 | Template for individual blog posts
103 |  | Blog Setup | Lead Capture Integration | 8 | 2 | Form for newsletter or lead capture
104 |  | SEO & Content | SEO Tools Setup | 8 | 3 | Install and configure SEO plugins/tools
105 |  | SEO & Content | Schema Markup | 8 | 3 | Add structured data/schema for SEO
106 |  | SEO & Content | Sitemap Generation | 8 | 1 | Generate XML sitemap
107 |  | SEO & Content | Robots.txt Setup | 8 | 1 | Configure robots.txt for crawling rules
108 |  | SEO & Content | Copywriting – Improve Existing Content | 8 | 3 | Edit and optimize current content
109 |  | SEO & Content | Copywriting – New Content (per 800 words) | 8 | 6 | Write new copy for a page (800 words)
110 |  | SEO & Content | Setup of URL redirects (301) | 8 | 2 | Setup of URL redirects (301) to maintain SEO and handle URL changes
111 |  | SEO & Content | Performance Core Web Vitals Optimization | 8 | 6 | Optimize site for LCP, CLS, and INP by improving loading speed, reducing layout shifts, optimizing assets, and ensuring smooth interactivity.
112 |  | Analytics & Tracking | Moderate Conversion tracking | 12 | 8 | Moderate (multiple events + testing + GA4 setup) Limit up to 8 events to configure and test.
113 |  | Analytics & Tracking | Basic conversion | 12 | 6 | Basic conversion tracking for forms (submission events only, no advanced tracking)
114 |  | Environment Setup | Hosting Setup & Configuration | 13 | 3 | Provision and configure a WordPress-ready hosting environment, including server setup, PHP and MySQL configuration, and domain connection. Configure performance settings (caching, memory limits), implement security best practices (firewall, SSL readiness, access controls), and ensure the environment is optimized for reliability, speed, and scalability.
115 |  | Environment Setup | WordPress Installation & Base Config | 13 | 2 | Install WordPress, configure core settings (permalinks, timezone, security basics), and prepare a clean foundation.
116 | 108: WordPress Installation | Environment Setup | Theme Setup (base theme / builder setup) | 13 | 3 | Install and configure theme or page builder, including global styles, layout settings, and reusable components.
117 | 108: WordPress Installation |  | Plugin Installation & Baseline Config | 13 | 3 | Install and configure core plugins (SEO, cache, security, forms). Includes existing plugins only; new plugin setup not included
118 |  | Environment Setup | User Roles & Permissions Setup | 13 | 2 | Define user roles (admin, editor, etc.), configure permissions, and enforce proper access control.
119 |  | Environment Setup | Local / Dev Environment Setup | 13 | 3 | Set up local development environment for safe development, including database, files, and tooling.
120 |  | Environment Setup | Environment Sync (Dev ↔ Staging) | 13 | 2 | Sync database between environments with URL replacement to maintain consistency across environments.
121 |  | Environment Setup | Staging Environment Setup | 13 | 4 | Create a staging site for QA/testing with production-like configuration and restricted access.
122 |  | Environment Setup | Domain Set-up | 13 | 2 | Point domain to hosting, configure DNS records, and ensure proper domain resolution.
123 |  | Deployment | Data migration / content import | 14 | 6 | Migrate existing content, database, and media into the new environment, ensuring structure and integrity are preserved.
124 |  | Pre-Launch QA | Final QA before go-live | 14 | 4 | Test functionality, responsiveness, forms, links, and cross-browser compatibility before launch.
125 |  | Backup Before Deploy | Full backup before deployment | 14 | 1 | Create full backup of database and files before deployment for rollback safety
126 | 122: Backup + 121: Final QA | Production Deployment | Deploy site to production | 14 | 4 | Deploy site from staging to production including database migration, file transfer, and validation
127 |  | URL/DB Sync | Update URLs and sync database | 14 | 2 | Replace staging URLs with production URLs and ensure database consistency.
128 |  | Cache/CDN Setup | Configure caching and CDN | 14 | 3 | Set up caching layers and CDN for faster global delivery and improved performance. Basic CDN setup (e.g., Cloudflare, no advanced edge rules)
129 | 123: Production Deployment | SSL & Mixed Content Fix | Fix SSL and mixed content issues | 14 | 2 | Ensure HTTPS is enforced and resolve any insecure resource loading issues.
130 |  | CMS Structure Setup | Setup CPTs, fields, content structure | 15 | 10 | Create custom post types, taxonomies, and fields to support structured, scalable content.
131 | 117: CMS Structure Setup | Dynamic Templates | Build dynamic templates (ACF/builder) | 15 | 14 | Develop reusable templates that dynamically pull content from fields for consistency and efficiency.
132 | 118: Dynamic Templates | Content Entry | Add content to pages | 15 | 2 | Populate pages with provided content, ensuring formatting, layout, and consistency with design.
133 | 119: Content Entry | Media Optimization | Optimize images and media | 15 | 3 | Compress, resize, and serve media in modern formats (e.g., WebP), implement lazy loading.
134 | 123-126: All deployment tasks | Post-Launch QA | QA and bug fixes after launch | 17 | 6 | Post-launch validation and quick resolution of any issues found in production.
135 |  | Performance Check | Verify speed and performance | 17 | 2 | Run performance tests and confirm site meets expected speed benchmarks.
136 |  | Tracking Verification | Test GA4 and tracking setup | 17 | 2 | Validate analytics tracking, events, and conversions to ensure accurate data collection.

## Squarespace
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services or Product Grid | 1 | 3 | Grid layout using Squarespace sections or summary blocks
3 |  | Homepage – Standard | Testimonials (Embed) | 1 | 3 | Testimonials via embed block or native content
4 |  | Homepage – Standard | Team Preview | 1 | 1.5 | Team member section using image + text blocks
5 |  | Homepage – Standard | Footer Layout | 1 | 1.5 | Footer navigation, contact, social links
6 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Hero with CTA using Squarespace buttons
7 |  | Homepage – Conversion | Benefits/Features | 1 | 3 | Feature sections using layout blocks
8 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Logos or badges using image blocks
9 |  | Homepage – Conversion | FAQ Section | 1 | 2 | Collapsible FAQ blocks
10 |  | Homepage – Standard | Pricing Tables | 1 | 4 | Pricing using columns/layout blocks
11 |  | Homepage – Standard | Galleries | 1 | 2 | Gallery block (grid/slider/lightbox)
12 |  | Homepage – Standard | Video Embeds | 1 | 1 | Video block (YouTube/Vimeo)
13 |  | Homepage – Standard | Donations / Payments | 1 | 4 | Squarespace Payments or Stripe integration
14 |  | Homepage – Standard | Use Cases | 1 | 2 | Content sections for use cases
15 |  | Homepage – Standard | Forms Spam Protection | 1 | 1 | Basic spam protection (Squarespace built-in)
16 |  | Homepage – Creative | Full-Screen Visuals | 3 | 6 | Full-width image sections
17 |  | Homepage – Creative | Parallax Effects | 3 | 3 | Built-in scroll effects (limited vs WP)
18 |  | Homepage – Creative | Hover Animations | 3 | 2 | Basic hover effects (native styles)
19 |  | Homepage – Creative | Creative Layouts | 3 | 4 | Custom section layouts using fluid engine
20 |  | Homepage – Creative | Portfolio Preview | 3 | 4 | Portfolio/gallery collection preview
21 |  | Homepage – Conversion | Lead Capture Form | 4 | 2 | Squarespace form block
22 |  | Integrations | Live Chat Integration | 4 | 2 | Embed third-party chat (Intercom, etc.)
23 |  | Integrations | Appointment Scheduling | 4 | 3 | Squarespace Scheduling or embed tool
24 |  | Integrations | Zapier Workflows | 4 | 4 | Zapier connection via form/email triggers
25 |  | Integrations | Basic API / Embed Integration | 4 | 6 | Embed external tools via code block
26 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 6 | Basic pages using sections
27 |  | Core Page - Landing Page | Conversion Landing Page | 1 | 6 | Structured conversion layout
28 |  | Core Page - Contact Page | Contact Page | 1 | 5 | Form + contact info layout
29 |  | Core Page - Detail Page | Blog/Service Detail | 1 | 5 | Blog or collection item template
30 |  | Forms – Standard | Standard Form Setup | 4 | 2 | Form with fields + email notifications
31 |  | Forms – Advanced | Storage & Notifications | 4 | 2 | Form submissions stored + email
32 |  | Members Area | Members Area Setup | 4 | 6 | Squarespace Member Areas setup
33 |  | Members Area | Basic Access Control | 4 | 4 | Restrict pages/content
34 |  | E-Commerce | Product Listings | 5 | 5 | Product collection setup
35 |  | E-Commerce | Product Detail Page | 5 | 5 | Product page layout
36 |  | E-Commerce | Cart Functionality | 5 | 3 | Built-in cart
37 |  | E-Commerce | Checkout Flow | 5 | 4 | Native checkout
38 |  | E-Commerce | Payments Setup | 5 | 3 | Stripe/PayPal via Squarespace
39 |  | E-Commerce | Shipping Setup | 5 | 4 | Shipping rules config
40 |  | E-Commerce | Tax Setup | 5 | 3 | Tax configuration
41 |  | E-Commerce | Featured Products Section | 5 | 4 | Product blocks on homepage
42 |  | E-Commerce | Promotional Banners | 5 | 3 | Sales banners using sections
43 |  | E-Commerce | Category Navigation | 5 | 4 | Product category organization
44 |  | E-Commerce | Customer Reviews (Basic) | 5 | 3 | Manual or embed-based reviews
45 |  | Analytics & Tracking | GA4 Setup | 7 | 2 | Google Analytics integration
46 |  | Analytics & Tracking | GTM Setup | 7 | 3 | Tag Manager install
47 |  | Analytics & Tracking | Basic Conversion Tracking | 12 | 4 | Form + button tracking
48 |  | Analytics & Tracking | Heatmaps | 7 | 1 | Hotjar or similar via embed
49 |  | Blog Setup | Blog Page Setup | 8 | 2 | Blog index page
50 |  | Blog Setup | Blog Post Template | 8 | 2 | Default post layout
51 |  | Blog Setup | Blog Lead Capture | 8 | 2 | Newsletter form
52 |  | SEO & Content | On-Page SEO Setup | 8 | 3 | Titles, meta, descriptions
53 |  | SEO & Content | Sitemap (Auto) | 8 | 0 | Auto-generated by Squarespace
54 |  | SEO & Content | Robots.txt (Basic) | 8 | 1 | Limited configuration
55 |  | SEO & Content | URL Redirects | 8 | 2 | Built-in redirect manager
56 |  | SEO & Content | Copywriting – Improve | 8 | 3 | Content optimization
57 |  | SEO & Content | Copywriting – New (800 words) | 8 | 6 | New content creation
58 |  | Performance | Basic Optimization | 7 | 3 | Image compression, layout cleanup
59 |  | Accessibility | ADA Basic | 4 | 4 | Alt text, contrast, structure
60 |  | Environment Setup | Squarespace Site Setup | 13 | 2 | Create site, basic config
61 |  | Environment Setup | Template & Styles Setup | 13 | 3 | Fonts, colors, global styles
62 |  | Environment Setup | Domain Connection | 13 | 2 | Connect domain
63 |  | Deployment | Content Migration (Manual) | 14 | 5 | Copy content into Squarespace
64 |  | Deployment | Pre-Launch QA | 14 | 3 | Responsive + functionality checks
65 |  | Deployment | Launch Site | 14 | 2 | Go live + domain switch
66 |  | Deployment | Post-Launch QA | 17 | 3 | Fix issues after launch
67 |  | Deployment | Tracking Verification | 17 | 2 | Confirm analytics + events

## Shopify
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services or Product Grid | 1 | 3 | Product/collection grid using Shopify sections
3 |  | Homepage – Standard | Testimonials | 1 | 3 | Testimonials via theme section or app
4 |  | Homepage – Standard | Team Preview | 1 | 2 | Team section using content blocks
5 |  | Homepage – Standard | Footer Layout | 1 | 2 | Footer with navigation, contact, socials
6 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Hero with CTA
7 |  | Homepage – Conversion | Benefits/Features | 1 | 3 | Features/benefits sections
8 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Logos, reviews, trust badges
9 |  | Homepage – Conversion | FAQ Section | 1 | 2 | Accordion FAQ
10 |  | Homepage – Conversion | Pricing Tables | 1 | 4 | Subscription or pricing layouts
11 |  | Homepage – E-Commerce | Featured Products | 5 | 4 | Featured products section
12 |  | Homepage – E-Commerce | Sales Banners | 5 | 3 | Promo banners
13 |  | Homepage – E-Commerce | Dynamic Product Feeds | 5 | 6 | Collections + filters
14 |  | Homepage – E-Commerce | Category Highlights | 5 | 4 | Collection highlights
15 |  | Homepage – E-Commerce | Customer Reviews | 5 | 5 | Product reviews via app
16 |  | Homepage – E-Commerce | Personalization Blocks | 5 | 6 | Recommended products (apps)
17 |  | Homepage – Creative | Full-Screen Visuals | 3 | 5 | Image-heavy layouts
18 |  | Homepage – Creative | Parallax Effects | 3 | 3 | Theme-based effects
19 |  | Homepage – Creative | Hover Animations | 3 | 3 | Theme/custom CSS
20 |  | Homepage – Creative | Creative Layouts | 3 | 5 | Custom sections or Liquid edits
21 |  | Homepage – Conversion | Lead Capture Form | 4 | 2 | Form or email signup
22 |  | Homepage – Conversion | Forms Spam Protection | 4 | 1 | Basic spam protection
23 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 6 | Content pages
24 |  | Core Page - Landing Page | Landing Page | 1 | 8 | Conversion-focused layout
25 |  | Core Page - Contact Page | Contact Page | 1 | 5 | Contact form + info
26 |  | Core Page - Blog Detail | Blog Post Template | 1 | 4 | Shopify blog template
27 |  | Forms – Standard | Form Setup | 4 | 3 | Basic forms + notifications
28 |  | Forms – Multi-Step | Multi-Step Form | 4 | 6 | Using apps (limited logic)
29 |  | Integrations | Appointment System | 4 | 3 | Calendly or booking app
30 |  | Integrations | Live Chat Integration | 4 | 2 | Chat widget/app
31 |  | Integrations | API Integration Basic | 4 | 10 | App or webhook-based
32 |  | Integrations | API Integration Complex | 4 | 20 | Custom app or middleware
33 |  | Integrations | Zapier Workflows | 4 | 5 | Automation workflows
34 |  | Integrations | Accessibility (Basic) | 4 | 5 | Theme adjustments
35 |  | Members / Accounts | Customer Accounts | 4 | 4 | Shopify customer accounts
36 |  | Members / Accounts | Profile Management | 4 | 4 | Account editing
37 |  | Members / Accounts | Restricted Content | 4 | 6 | Apps or Liquid logic
38 |  | E-Commerce Core | Product Template | 5 | 6 | Product page template
39 |  | E-Commerce Core | Cart Functionality | 5 | 4 | Built-in cart
40 |  | E-Commerce Core | Checkout Flow | 5 | 4 | Shopify checkout (limited customization)
41 |  | E-Commerce Core | Shipping Rules | 5 | 4 | Shipping setup
42 |  | E-Commerce Core | Payment Gateway Integration | 5 | 3 | Shopify Payments / PayPal
43 |  | E-Commerce Core | Tax Calculator | 5 | 2 | Built-in taxes
44 |  | Advanced E-Commerce | Product Options / Variants | 6 | 6 | Variants or apps
45 |  | Advanced E-Commerce | Product Customizer (Basic) | 6 | 12 | Product customization apps
46 |  | Advanced E-Commerce | Product Customizer (Advanced) | 6 | 25 | Advanced configurator apps
47 |  | Advanced E-Commerce | Subscriptions | 6 | 6 | Subscription apps
48 |  | Advanced E-Commerce | Discount Logic | 6 | 4 | Discount rules
49 |  | Performance | Basic Optimization | 7 | 4 | Image + theme optimization
50 |  | Analytics | GA4 Setup | 7 | 2 | Add GA4
51 |  | Analytics | GTM Setup | 7 | 3 | Add GTM
52 |  | Analytics | Conversion Tracking | 7 | 5 | Events + testing
53 |  | Blog | Blog Setup | 8 | 2 | Blog listing
54 |  | Blog | Single Post Template | 8 | 1 | Default template
55 |  | Blog | Lead Capture Integration | 8 | 2 | Email signup
56 |  | SEO | Basic SEO Setup | 8 | 2 | Titles + meta
57 |  | SEO | Schema (Basic) | 8 | 2 | Theme/app-based schema
58 |  | SEO | Sitemap (Auto) | 8 | 0 | Auto-generated
59 |  | SEO | URL Redirects | 8 | 2 | Redirects setup
60 |  | SEO | Content Optimization | 8 | 3 | On-page SEO
61 |  | Environment Setup | Shopify Store Setup | 13 | 2 | Create store
62 |  | Environment Setup | Theme Setup & Customization | 13 | 5 | Theme + sections + styling
63 |  | Environment Setup | Domain Setup | 13 | 2 | Connect domain
64 |  | Content Entry | Content Upload | 15 | 3 | Add content/products
65 |  | Content Entry | Media Optimization | 15 | 2 | Image optimization
66 |  | Pre-Launch QA | QA Review | 14 | 4 | Test store, checkout, responsiveness
67 |  | Deployment | Go Live | 14 | 2 | Launch store
68 |  | Post-Launch | QA Fixes | 17 | 4 | Bug fixes
69 |  | Post-Launch | Tracking Verification | 17 | 2 | Verify analytics

## WIX
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services or Product Grid | 1 | 3 | Grid using Wix repeater/layout tools
3 |  | Homepage – Standard | Testimonials | 1 | 3 | Testimonials via sections or apps
4 |  | Homepage – Standard | Team Preview | 1 | 2 | Team section using repeaters
5 |  | Homepage – Standard | Footer Layout | 1 | 2 | Footer with nav, contact, socials
6 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Hero with CTA
7 |  | Homepage – Conversion | Benefits/Features | 1 | 3 | Content sections
8 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Logos/reviews
9 |  | Homepage – Conversion | FAQ Section | 1 | 2 | Collapsible FAQ
10 |  | Homepage – Standard | Pricing Tables | 1 | 4 | Pricing layout sections
11 |  | Homepage – Standard | Galleries | 1 | 2 | Wix gallery
12 |  | Homepage – Standard | Video Embeds | 1 | 1 | Video blocks
13 |  | Homepage – Standard | Payments / Donations | 1 | 4 | Wix Payments / Stripe / PayPal
14 |  | Homepage – Standard | Use Cases | 1 | 2 | Content sections
15 |  | Homepage – Standard | Map / Location Section | 1 | 2 | Wix map embed
16 |  | Homepage – Creative | Full-Screen Visuals | 3 | 5 | Image-heavy sections
17 |  | Homepage – Creative | Parallax Effects | 3 | 3 | Built-in scroll effects
18 |  | Homepage – Creative | Hover Animations | 3 | 3 | Basic interactions
19 |  | Homepage – Creative | Creative Layouts | 3 | 5 | Flexible editor layouts
20 |  | Homepage – Conversion | Lead Capture Form | 4 | 2 | Wix Forms
21 |  | Homepage – Conversion | Forms Spam Protection | 4 | 1 | Built-in spam protection
22 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 6 | Content pages
23 |  | Core Page - Landing Page | Landing Page | 1 | 7 | Conversion-focused layout
24 |  | Core Page - Contact Page | Contact Page | 1 | 5 | Form + contact info
25 |  | Core Page - Blog Detail | Blog Post Template | 1 | 4 | Wix blog
26 |  | Forms – Standard | Form Setup | 4 | 3 | Wix form setup + notifications
27 |  | Forms – Multi-Step | Multi-Step Form | 4 | 6 | Wix forms or apps (limited logic)
28 |  | Integrations | Appointment System | 4 | 3 | Wix Bookings or embed
29 |  | Integrations | Live Chat Integration | 4 | 2 | Wix Chat or app
30 |  | Integrations | API Integration Basic | 4 | 10 | Velo or webhook
31 |  | Integrations | API Integration Complex | 4 | 18 | Velo custom logic
32 |  | Integrations | Zapier Workflows | 4 | 5 | Automation via Zapier
33 |  | Integrations | Accessibility (Basic) | 4 | 5 | Wix accessibility tools
34 |  | Members Area | Member Login | 4 | 4 | Wix Members Area
35 |  | Members Area | Profile Management | 4 | 4 | User profiles
36 |  | Members Area | Restricted Content | 4 | 6 | Gated pages/content
37 |  | E-Commerce | Featured Products | 5 | 4 | Product showcase
38 |  | E-Commerce | Sales Banners | 5 | 3 | Promo banners
39 |  | E-Commerce | Product Listings | 5 | 5 | Wix Stores pages
40 |  | E-Commerce | Category Pages | 5 | 4 | Collections/categories
41 |  | E-Commerce | Product Detail Page | 5 | 5 | Product page
42 |  | E-Commerce | Cart & Checkout | 5 | 4 | Built-in checkout
43 |  | E-Commerce | Payments Setup | 5 | 3 | Wix Payments / Stripe
44 |  | E-Commerce | Shipping Setup | 5 | 3 | Shipping rules
45 |  | E-Commerce | Taxes Setup | 5 | 2 | Tax config
46 |  | Advanced | Wix Dynamic Content (CMS) | 6 | 8 | Wix CMS collections + repeaters
47 |  | Advanced | Custom Logic (Velo) | 6 | 12 | Custom interactions using Velo
48 |  | Advanced | Filters & Search | 6 | 8 | Dataset filtering/search
49 |  | Advanced | Basic Product Customization | 6 | 10 | Product options or apps
50 |  | Performance | Basic Optimization | 7 | 4 | Image + layout optimization
51 |  | Analytics | GA4 Setup | 7 | 2 | Add GA4
52 |  | Analytics | GTM Setup | 7 | 3 | Add GTM
53 |  | Analytics | Conversion Tracking | 7 | 5 | Events + testing
54 |  | Blog | Blog Setup | 8 | 2 | Blog listing
55 |  | Blog | Single Post Template | 8 | 1 | Default template
56 |  | Blog | Lead Capture Integration | 8 | 2 | Newsletter form
57 |  | SEO | Basic SEO Setup | 8 | 2 | Titles + meta
58 |  | SEO | Schema (Basic) | 8 | 2 | Wix SEO tools
59 |  | SEO | Sitemap (Auto) | 8 | 0 | Auto-generated
60 |  | SEO | URL Redirects | 8 | 2 | Redirect manager
61 |  | SEO | Content Optimization | 8 | 3 | On-page SEO
62 |  | Environment Setup | Wix Site Setup | 13 | 2 | Create site
63 |  | Environment Setup | Template & Design Setup | 13 | 4 | Editor + styles
64 |  | Environment Setup | Domain Setup | 13 | 2 | Connect domain
65 |  | Content Entry | Content Upload | 15 | 3 | Add content/products
66 |  | Content Entry | Media Optimization | 15 | 2 | Image optimization
67 |  | Pre-Launch QA | QA Review | 14 | 4 | Test responsiveness + features
68 |  | Deployment | Go Live | 14 | 2 | Publish site
69 |  | Post-Launch | QA Fixes | 17 | 4 | Bug fixes
70 |  | Post-Launch | Tracking Verification | 17 | 2 | Verify analytics

## PHPHTMLCSS
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services or Product Grid | 1 | 3 | Custom grid layout for services/products
3 |  | Homepage – Standard | Testimonials Slider (Dynamic) | 1 | 8 | Dynamic testimonials via DB/API
4 |  | Homepage – Standard | Testimonials (Embed) | 1 | 3 | Embedded testimonials
5 |  | Homepage – Standard | Team Preview | 1 | 1.5 | Team members section
6 |  | Homepage – Standard | Footer Layout | 1 | 1.5 | Footer with navigation and contact info
7 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Hero with CTA
8 |  | Homepage – Conversion | Benefits/Features | 1 | 3 | Feature sections
9 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Logos and credibility indicators
10 |  | Homepage – Conversion | FAQ Section | 1 | 2 | FAQ block
11 |  | Homepage – Standard | Pricing Tables | 1 | 4 | Pricing layout
12 |  | Homepage – Standard | Galleries | 1 | 2 | Custom gallery
13 |  | Homepage – Standard | Video Embeds | 1 | 1 | Video embeds
14 |  | Homepage – Standard | Payment / Contribution Module | 1 | 6 | Stripe/PayPal integration
15 |  | Homepage – Standard | Use Cases | 1 | 2 | Use case sections
16 |  | Homepage – Multi-Industry | Industry Selector | 1 | 8 | Dynamic selector
17 |  | Homepage – Multi-Industry | Location Selector | 1 | 8 | Location-based content
18 |  | Homepage – Multi-Industry | Dynamic Content Sections | 1 | 10 | Conditional rendering
19 |  | Homepage – Multi-Industry | Interactive Location Finder | 1 | 12 | Map-based finder
20 |  | Homepage – Multi-Industry | Multi-Audience Messaging | 1 | 10 | Personalized content
21 |  | Homepage – Advanced Dynamic | Custom-Coded Blocks | 2 | 15 | Reusable components
22 |  | Homepage – Advanced Dynamic | Search Bar with Filters | 2 | 18 | Advanced filtering/search
23 |  | Homepage – Advanced Dynamic | API-Driven Content | 2 | 15 | External API integrations
24 |  | Homepage – Advanced Dynamic | Interactive Dashboard | 2 | 20 | Charts and data dashboards
25 |  | Homepage – Creative | Full-Screen Visuals | 3 | 6 | Image-heavy layouts
26 |  | Homepage – Creative | Parallax Effects | 3 | 5 | Scroll animations
27 |  | Homepage – Creative | Hover Animations | 3 | 4 | Custom interactions
28 |  | Homepage – Creative | Creative Grid Layouts | 3 | 5 | Advanced layouts
29 |  | Homepage – Creative | Portfolio Gallery Preview | 3 | 5 | Portfolio display
30 |  | Homepage – Conversion | Lead Capture Form | 4 | 3 | Custom form (frontend + backend)
31 |  | Homepage – Conversion | Forms Spam Protection | 4 | 2 | reCAPTCHA / validation
32 |  | Homepage – Advanced Dynamic | Multi-Step Wizard Form | 4 | 18 | Custom multi-step form
33 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 8 | Content page
34 |  | Core Page - Landing Page | Landing Page | 1 | 8 | Conversion-focused page
35 |  | Core Page - Contact Page | Contact Page | 1 | 6 | Form + contact details
36 |  | Core Page - Detail Pages | Detail Page Template | 1 | 6 | Dynamic template
37 |  | Forms – Standard | Form Layout | 4 | 2 | Frontend form UI
38 |  | Forms – Standard | Validation & Error Handling | 4 | 2 | Client + server validation
39 |  | Forms – Standard | Email Notification | 4 | 2 | Send submission emails
40 |  | Forms – Multi-Step | Multi-Step Layout | 4 | 4 | Multi-step UI
41 |  | Forms – Multi-Step | Branch Logic Implementation | 4 | 4 | Conditional logic
42 |  | Forms – Multi-Step | Submission Handling | 4 | 2 | Process/store submissions
43 |  | Forms – CRM Integration | CRM API Setup | 4 | 4 | Connect to CRM
44 |  | Forms – CRM Integration | Data Mapping | 4 | 2 | Map fields
45 |  | Forms – CRM Integration | Error Handling & Logging | 4 | 2 | Logging + fail handling
46 |  | Integrations | Appointment System | 4 | 4 | Booking system
47 |  | Integrations | Live Chat Integration | 4 | 2 | Chat widget
48 |  | Integrations | API Integration Basic | 4 | 12 | Simple API
49 |  | Integrations | API Integration Complex | 4 | 25 | Advanced API
50 |  | Integrations | Zapier Workflows | 4 | 6 | Automation
51 |  | Integrations | Accessibility (ADA) Basic | 4 | 6 | Basic compliance
52 |  | Integrations | Accessibility (ADA) Strict | 4 | 25 | Full WCAG
53 |  | Member Login | Login System | 4 | 10 | Auth system
54 |  | Member Login | Profile Management | 4 | 10 | User profiles
55 |  | Member Login | Role-Based Content | 4 | 12 | Permissions system
56 |  | Member Login | Document Portal | 4 | 20 | File portal
57 |  | E-Commerce | Product Template | 5 | 8 | Product page template
58 |  | E-Commerce | Product Listings | 5 | 8 | Category/shop pages
59 |  | E-Commerce | Cart Functionality | 5 | 6 | Session/cart system
60 |  | E-Commerce | Checkout Flow | 5 | 10 | Custom checkout
61 |  | E-Commerce | Shipping Rules | 5 | 6 | Shipping logic
62 |  | E-Commerce | Payment Gateway Integration | 5 | 6 | Stripe/PayPal
63 |  | E-Commerce | Tax Calculator | 5 | 5 | Dynamic tax logic
64 |  | E-Commerce | Customer Reviews | 5 | 6 | Review system
65 |  | E-Commerce | Personalization | 5 | 8 | Recommended products
66 |  | Configurator – Basic 2D | Color Change Feature | 6 | 15 | Dynamic UI updates
67 |  | Configurator – Basic 2D | Shape Options | 6 | 20 | Option selection
68 |  | Configurator – Basic 2D | Static Preview Rendering | 6 | 30 | Image generation
69 |  | Configurator – Advanced 2D | Pattern Library | 6 | 30 | Pattern system
70 |  | Configurator – Advanced 2D | Upload & Download Assets | 6 | 30 | File handling
71 |  | Configurator – Advanced 2D | Screenshot Capture | 6 | 40 | Capture previews
72 |  | Configurator – 3D | WebGL Viewer | 6 | 50 | 3D rendering
73 |  | Configurator – Full Builder | Quote Generation | 6 | 40 | Dynamic pricing
74 |  | Configurator – Full Builder | Saved Designs | 6 | 40 | User saved states
75 |  | Configurator – Features | Logo Upload | 6 | 12 | File upload
76 |  | Configurator – Features | Size Calculator | 6 | 15 | Calculation logic
77 |  | Configurator – Features | Shareable Link | 6 | 12 | Share state via URL
78 |  | Configurator – Features | Admin Dashboard | 6 | 40 | Admin panel
79 |  | Performance & Security | SSL Setup | 7 | 1 | SSL configuration
80 |  | Performance & Security | Caching & Optimization | 7 | 10 | Server + frontend optimization
81 |  | Performance & Security | Backup & Versioning | 7 | 4 | Backup systems
82 |  | Analytics & Tracking | GA4 Setup | 7 | 2 | Analytics setup
83 |  | Analytics & Tracking | GTM Setup | 7 | 3 | Tag manager
84 |  | Analytics & Tracking | Heatmaps | 7 | 2 | User tracking
85 |  | Blog Setup | Blog Listing | 8 | 4 | Blog index
86 |  | Blog Setup | Single Article Template | 8 | 3 | Blog post template
87 |  | Blog Setup | Lead Capture | 8 | 2 | Newsletter form
88 |  | SEO & Content | SEO Setup | 8 | 4 | On-page SEO
89 |  | SEO & Content | Schema Markup | 8 | 4 | Structured data
90 |  | SEO & Content | Sitemap Generation | 8 | 2 | XML sitemap
91 |  | SEO & Content | Robots.txt Setup | 8 | 1 | Crawl rules
92 |  | SEO & Content | Copy Optimization | 8 | 4 | Improve content
93 |  | SEO & Content | New Copy (800 words) | 8 | 6 | Content writing
94 |  | SEO & Content | URL Redirects | 8 | 2 | 301 redirects
95 |  | Environment Setup | Hosting Setup | 13 | 4 | Server setup
96 |  | Environment Setup | Base Project Setup | 13 | 3 | PHP structure
97 |  | Environment Setup | Routing Setup | 13 | 4 | URL routing
98 |  | Environment Setup | Database Setup | 13 | 4 | DB schema
99 |  | Environment Setup | Auth System Setup | 13 | 6 | User auth system
100 |  | Environment Setup | Dev Environment | 13 | 3 | Local setup
101 |  | Deployment | Data Migration | 14 | 6 | Content migration
102 |  | Deployment | Staging Setup | 14 | 4 | Staging environment
103 |  | Deployment | Domain Setup | 14 | 2 | DNS config
104 |  | Deployment | Production Deployment | 14 | 5 | Launch
105 |  | Deployment | URL Sync | 14 | 2 | URL updates
106 |  | Deployment | CDN Setup | 14 | 4 | Cloudflare/CDN
107 |  | Deployment | SSL Fixes | 14 | 2 | HTTPS fixes
108 |  | Pre-Launch QA | Final QA | 14 | 5 | Full testing
109 |  | Post-Launch | QA Fixes | 17 | 6 | Bug fixes
110 |  | Post-Launch | Performance Check | 17 | 3 | Speed testing
111 |  | Post-Launch | Tracking Verification | 17 | 2 | Verify analytics
112 |  | Backend | Database Setup & Configuration | 18 | 6 | Create database, users, permissions, connection setup
113 |  | Backend | Database Schema Design | 18 | 10 | Design tables, relationships, normalization
114 |  | Backend | Data Modeling (Entities & Relationships) | 18 | 12 | Define structure for features (users, products, etc.)
115 |  | Backend | Migrations / Versioning | 18 | 6 | Setup schema version control and migrations
116 |  | Backend | ORM / Query Layer Setup | 18 | 8 | Setup database abstraction or query handling
117 |  | Backend | Seed Data / Initial Data Setup | 18 | 4 | Populate initial data for testing/dev
118 |  | Backend | Database Optimization | 18 | 8 | Indexes, query optimization, performance tuning

## React.js and Next.js
id | Dependencies | module | name | category_id | base_hours | description
1 |  | Homepage – Standard | Hero Section | 1 | 2 | Hero section and headline
2 |  | Homepage – Standard | Services / Product Grid | 1 | 3 | Grid for services/products
3 |  | Homepage – Standard | Testimonials Slider (Dynamic) | 1 | 8 | API-driven testimonials
4 |  | Homepage – Standard | Testimonials (Embed) | 1 | 3 | Embedded testimonials
5 |  | Homepage – Standard | Team Preview | 1 | 1.5 | Team section
6 |  | Homepage – Standard | Footer Layout | 1 | 1.5 | Footer with nav/contact
7 |  | Homepage – Conversion | Strong Hero Offer | 1 | 4 | Hero with CTA
8 |  | Homepage – Conversion | Benefits / Features | 1 | 3 | Feature sections
9 |  | Homepage – Conversion | Social Proof / Trust Badges | 1 | 2 | Logos and trust elements
10 |  | Homepage – Conversion | FAQ Section | 1 | 2 | FAQ block
11 |  | Homepage – Standard | Pricing Tables | 1 | 4 | Pricing layout
12 |  | Homepage – Standard | Galleries | 1 | 2 | Image galleries
13 |  | Homepage – Standard | Video Embeds | 1 | 1 | Video embeds
14 |  | Homepage – Standard | Payment / Contribution Module | 1 | 5 | Stripe/PayPal plugin-based
15 |  | Homepage – Standard | Use Cases | 1 | 2 | Use case sections
16 |  | Homepage – Multi-Industry | Industry Selector | 1 | 8 | Multi-industry selector
17 |  | Homepage – Multi-Industry | Location Selector | 1 | 8 | Location selector
18 |  | Homepage – Multi-Industry | Dynamic Content Sections | 1 | 10 | Conditional content
19 |  | Homepage – Multi-Industry | Interactive Location Finder | 1 | 12 | Map-based finder
20 |  | Homepage – Multi-Industry | Multi-Audience Messaging | 1 | 12 | Audience targeting
21 |  | Homepage – Advanced Dynamic | Custom-Coded Blocks | 2 | 15 | Reusable custom blocks
22 |  | Homepage – Advanced Dynamic | Search Bar with Filters | 2 | 18 | Advanced filtering
23 |  | Homepage – Advanced Dynamic | API-Driven Content | 2 | 15 | External API data
24 |  | Homepage – Advanced Dynamic | Interactive Dashboard | 2 | 18 | Data dashboards
25 |  | Homepage – Creative | Full-Screen Visuals | 3 | 6 | Image-heavy design
26 |  | Homepage – Creative | Parallax Effects | 3 | 5 | Scroll animations
27 |  | Homepage – Creative | Hover Animations | 3 | 4 | Interactive hover states
28 |  | Homepage – Creative | Creative Grid Layouts | 3 | 5 | Custom layouts
29 |  | Homepage – Creative | Portfolio Gallery Preview | 3 | 5 | Portfolio section
30 |  | Homepage – Conversion | Lead Capture Form | 4 | 2 | Standard form (no CRM)
31 |  | Homepage – Conversion | Forms Spam Protection (reCAPTCHA) | 4 | 1 | Spam prevention
32 |  | Homepage – Advanced Dynamic | Multi-Step Wizard Form | 4 | 20 | Advanced multi-step form
33 |  | Core Page - Standard | Standard Page (About, Services) | 1 | 8 | Content page
34 |  | Core Page - Landing Page | Conversion Page | 1 | 8 | Landing page layout
35 |  | Core Page - Contact Page | Contact Page | 1 | 6 | Contact form + details
36 |  | Core Page - Detail Pages | Detail Template (Blog/Service) | 1 | 6 | Dynamic template
37 |  | Forms – Standard | Form Setup | 4 | 3 | Layout, validation, email
38 |  | Forms – Multi-Step | Multi-Step Layout | 4 | 4 | Multi-step UI
39 |  | Forms – Multi-Step | Branch Logic Implementation | 4 | 4 | Conditional logic
40 |  | Forms – Multi-Step | Submission Handling | 4 | 2 | Store/process submissions
41 |  | Forms – CRM Integration | CRM API Setup | 4 | 4 | CRM connection
42 |  | Forms – CRM Integration | Data Mapping | 4 | 2 | Field mapping
43 |  | Forms – CRM Integration | Error Handling & Logging | 4 | 2 | Error handling
44 |  | Integrations | Appointment System | 4 | 3 | Booking plugin
45 |  | Integrations | Live Chat Integration | 4 | 2 | Chat widget
46 |  | Integrations | API Integration Basic | 4 | 12 | Simple API
47 |  | Integrations | API Integration Complex | 4 | 25 | Advanced API
48 |  | Integrations | Zapier Workflows | 4 | 6 | Automation
49 |  | Integrations | Accessibility (ADA) Basic | 4 | 6 | Basic compliance
50 |  | Integrations | Accessibility (ADA) Strict Compliance | 4 | 25 | Full WCAG
51 |  | Member Login | Basic Login System | 4 | 10 | Login/register
52 |  | Member Login | Profile Management | 4 | 10 | User profiles
53 |  | Member Login | Role-Based Content | 4 | 12 | Access control
54 |  | Member Login | Document Portal Setup | 4 | 20 | Document portal
55 |  | E-Commerce | Product Template | 5 | 7 | Product page template
56 |  | E-Commerce | Featured Products | 5 | 6 | Homepage products
57 |  | E-Commerce | Sales Banners | 5 | 5 | Promo banners
58 |  | E-Commerce | Dynamic Product Feeds | 5 | 8 | Product listings
59 |  | E-Commerce | Category Highlights | 5 | 6 | Product categories
60 |  | E-Commerce | Customer Reviews | 5 | 6 | Reviews
61 |  | E-Commerce | Personalization Blocks | 5 | 6 | Recommendations
62 |  | E-Commerce | Cart Functionality | 5 | 5 | Add to cart
63 |  | E-Commerce | Checkout Flow | 5 | 8 | Checkout page
64 |  | E-Commerce | Shipping Rules | 5 | 6 | Shipping setup
65 |  | E-Commerce | Payment Gateway Integration | 5 | 5 | Stripe/PayPal
66 |  | E-Commerce | Tax Calculator | 5 | 4 | Tax logic
67 |  | E-Commerce | Product Variations Setup | 5 | 3 | Configure product variations (size, color, attributes)
68 |  | 68: Variations | Advanced Product Options (Plugin) | 5 | 6 | Custom fields/options via plugin
69 |  | 68: Options | Product Add-Ons (Conditional Logic) | 5 | 8 | Add-ons with logic via plugin
70 |  | 62-66 Required | Subscriptions Setup | 5 | 6 | Recurring payments (plugin)
71 |  | 62-66 Required | Discount Rules / Coupons Setup | 5 | 4 | Coupons and promos
72 |  | 71: Discounts | Advanced Pricing Rules (Plugin) | 5 | 8 | Dynamic/role pricing
73 |  | 55-66 Required | Product Bundles / Packages | 5 | 6 | Bundled products
74 |  | E-Commerce | Wishlist Functionality | 5 | 4 | Wishlist plugin
75 |  | E-Commerce | Product Filtering (Advanced) | 5 | 6 | Advanced filters plugin
76 |  | Configurator – Basic | Color Change Feature | 6 | 15 | Color switching
77 |  | Configurator – Basic | Shape Options | 6 | 20 | Shape selection
78 |  | Configurator – Basic | Static Preview Rendering | 6 | 30 | Preview images
79 |  | Configurator – Advanced | Pattern Library | 6 | 30 | Pattern system
80 |  | Configurator – Advanced | Upload & Download Assets | 6 | 30 | File handling
81 |  | Configurator – Advanced | Screenshot Capture | 6 | 40 | Capture designs
82 |  | Configurator – 3D | Camera Controls | 6 | 40 | 3D camera
83 |  | Configurator – 3D | 3D Asset Integration | 6 | 50 | 3D models
84 |  | Configurator – 3D | Real-Time Rendering | 6 | 55 | Real-time visuals
85 |  | Configurator – Full Builder | Template Setup | 6 | 80 | Custom builder
86 |  | Configurator – Full Builder | Measurement Tools | 6 | 80 | Dimension tools
87 |  | Configurator – Full Builder | Quote Generation | 6 | 80 | Dynamic pricing
88 |  | Configurator – Full Builder | Saved Designs | 6 | 80 | User saves
89 |  | Configurator – Features | Logo Upload | 6 | 12 | Upload logos
90 |  | Configurator – Features | Size Calculator | 6 | 15 | Size logic
91 |  | Configurator – Features | Shareable Link | 6 | 12 | Share links
92 |  | Configurator – Features | Admin Dashboard | 6 | 44 | Admin tools
93 |  | Performance & Security | SSL Configuration | 7 | 1 | SSL setup
94 |  | Performance & Security | Caching & Optimization | 7 | 8 | Caching + speed
95 |  | Performance & Security | Backup & Versioning | 7 | 2 | Backups
96 |  | Analytics & Tracking | GA4 Setup | 7 | 2 | Analytics
97 |  | Analytics & Tracking | GTM Setup | 7 | 3 | Tag manager
98 |  | Analytics & Tracking | Heatmaps | 7 | 1 | Heatmaps
99 |  | Analytics & Tracking | Conversion Tracking (Basic) | 12 | 6 | Form tracking
100 |  | Analytics & Tracking | Conversion Tracking (Moderate) | 12 | 8 | Events + testing
101 |  | Blog Setup | Blog Listing Page | 8 | 2 | Blog index
102 |  | Blog Setup | Single Article Template | 8 | 2 | Post template
103 |  | Blog Setup | Lead Capture Integration | 8 | 2 | Newsletter form
104 |  | SEO & Content | SEO Tools Setup | 8 | 3 | SEO plugin config
105 |  | SEO & Content | Schema Markup | 8 | 3 | Structured data
106 |  | SEO & Content | Sitemap Generation | 8 | 1 | XML sitemap
107 |  | SEO & Content | Robots.txt Setup | 8 | 1 | Crawl rules
108 |  | SEO & Content | Content Optimization | 8 | 3 | Improve content
109 |  | SEO & Content | New Content (800 words) | 8 | 6 | Copywriting
110 |  | SEO & Content | URL Redirects (301) | 8 | 2 | Redirects
111 |  | SEO & Content | Core Web Vitals Optimization | 8 | 6 | Performance SEO
112 |  | Environment Setup | Hosting Setup | 13 | 3 | Server setup
113 |  | Environment Setup | WordPress Installation | 13 | 2 | WP install
114 |  | Environment Setup | Theme / Builder Setup | 13 | 3 | Theme config
115 |  | Environment Setup | Plugin Setup | 13 | 3 | Core plugins
116 |  | Environment Setup | User Roles & Permissions | 13 | 2 | Access setup
117 |  | Environment Setup | Local / Dev Setup | 13 | 3 | Local env
118 |  | Environment Setup | Environment Sync | 13 | 2 | Dev ↔ staging
119 |  | Environment Setup | Staging Setup | 13 | 4 | Staging site
120 |  | Environment Setup | Domain Setup | 13 | 2 | DNS config
121 |  | CMS Structure Setup | CPT & Fields Setup | 15 | 10 | Custom post types
122 |  | Dynamic Templates | Dynamic Template Build | 15 | 14 | ACF/templates
123 |  | Content Entry | Content Upload | 15 | 2 | Add content
124 |  | Content Entry | Media Optimization | 15 | 3 | Image optimization
125 |  | Deployment | Data Migration | 14 | 6 | Migration
126 |  | Deployment | Pre-Launch QA | 14 | 4 | Testing
127 |  | Deployment | Backup Before Deploy | 14 | 1 | Backup
128 |  | Deployment | Production Deployment | 14 | 4 | Launch
129 |  | Deployment | URL Sync | 14 | 2 | URL updates
130 |  | Deployment | CDN Setup | 14 | 3 | CDN
131 |  | Deployment | SSL Fixes | 14 | 2 | HTTPS fixes
132 |  | Post-Launch | QA & Bug Fixes | 17 | 6 | Fixes
133 |  | Post-Launch | Performance Check | 17 | 2 | Speed check
134 |  | Post-Launch | Tracking Verification | 17 | 2 | Verify analytics
121 |  | Backend | Database Setup & Configuration | 18 | 4 | Set up database, configure tables, users, and connections
122 |  | Backend | Custom Database Schema (if needed) | 18 | 8 | Create custom tables or extend schema for advanced features
123 |  | Backend | Data Modeling (CPT / ACF Structure) | 18 | 10 | Structure content using custom post types and fields

## more logic
Global Add-ons |  | Notes
If simple project: |  | Overide options
pm_hours = total_hours × 0.10 (10% of total hours)
else:
pm_hours = total_hours x 0.15 (15% of total hours)
responsive = total_dev_hours × 0.25
Need to add hours at the very end
design_hours = adjusted_dev_hours × 0.35
qa_hours = (adjusted_dev_hours + design_hours) × 0.2
Need to be able to multiply task per order
Input of pages that are similar same layout different content 3 hours discount
adjusted_page_hours = base_page_hours × reuse_factor
First page = 100%
Similar pages = 0.7 (Deduct)
if CMS = true:
cms_hours = cms_setup(6) + cms_modeling(12) + dynamic_template(18) + admin_ux(6)
else:
cms_hours = 0
Additional logic 5/12/26
Abby [2:52 PM]
so Jeff, I am thinking of each tasks we can add a dropdown either
[2:53 PM]
then we will add global ad-on that if the requirements is not clear they will check that button or choose then the multiplier will all be converted to Advanced
[2:54 PM]
Basic → 1.0
Advanced → 1.5
Custom → 2.0
Platform Options:
- WordPress
- Shopify
- Wix
- Squarespace
- Custom (PHP)
- Custom (React / Next.js)
And also add a dependencies - so what it does is if they chose a task | it would suggest that to check if they missed something...because if they chose any from 42-44 but none of the forms were chosen they are probablby missing a task